## Getting Started
This tool is an Excel-based spreadsheet that provides a framework, along with key tasks for implemeting a community's asset management program.
The template consists of the following three worksheets:
Getting Started
1. Example Annual Calendar
2. Annual Calendar Template
Introduction
This template illustrates, using GANTT chart, the annual (and 5 year) cycle of ongoing asset management practices required for implementing a program.
1. Example Annual Calendar
The example annual calendar illustrates the annual meetings, milestones, deliverables that make up the implementation actions for the community's asset managemnet program. It also includes key 5 year processes.
2. Annual Calendar Template
This template has been prepared so communities can build their own annual calendar of impelemtation actions. Alternately, a copy can be made of the Example Annnual Calendar and then adjustments to tailor the framework to the community's needs.

## 1. Example Annual Calendar
EXAMPLE Implementation Schedule
Legend
Five-Year Process
|  | INFORMATION | Key Actions
Milestone
| Implementation Task |  | JAN |  | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEPT | OCT | NOV | DEC | Deliverable
Meeting
Strategy & Planning | Service Levels | For current year(2018) | bar: FEB to AUG
| Risks | [14 empty] | Annual Action Details | bar: FEB
| Five-Year Capital Planning Strategy | For next year (2019) | [13 empty] | Level of Service Performance Reports | 1 | TCA Report | 12 | bar: FEB to JUN
| Prepare Corporate Annual Report | For current year (2018) | [13 empty] | Update Levels of Service Matrix | 2 | Audited Financial Statement | 13 | bar: MAY to JUN
| Asset Management Plan | Five year cycle. |  |  | MAY: MAJOR UPDATE EVERY FIVE YEARS | Annual Risk and Levels of Service Check-In | 3 | Budget Presentation to Council | 14
Information | Quality Assurance / Quality Control | Annual check; Five year review |  |  | APR: STANDARDS TO BE REVIEWED EVERY FIVE YEARS | Analysis of capital planning needs | 4 | Preparation of Five Year Financial Plan | 15
| Inventory Mangagement | Ongoing process (2018) | [13 empty] | 5 year Plan Capital Review Meeting | 5 | Council Approval of Five Year Financial Plan | 16
Financial Planning & Management | TCA Reconciliation | Info from prev. year (2017) | [13 empty] | 20-Year Capital Planning Meeting | 6 | Confirm Communication Objectives | 17 | bar: FEB to MAR; OCT to DEC
| Audited Financial Statements | Info. from prev. year (2017) | [13 empty] | Prepare Annual Report | 7 | Communication Strategy Review | 18 | bar: FEB to MAY
| Budget | For current fiscal year (2018) |  |  | JUL: REVIEW LTFP | Final Asset Management Plan(s) | 8 | Annual Communication Strategy | 19
Communications | Communication Strategy | For current year (2018) | [13 empty] | Draft Asset Management Plan(s) | 9 | Quarterly Communication Initiatives | 20 | bar: FEB to APR; NOV to DEC
| Public Engagement / Consultation | Ongoing process (2018) | [13 empty] | Inventory QA/QC Check | 10
| Linkages with Corporate Plans and Strategies | For future years (2019+) |  | INTEGRATION AS PLANS AND POLICIES ARE UPDATED THROUGHOUT THE YEAR | [11 empty] | Annual Inventory Check | 11
5
9
8
10
16
13
20
20
20
15
7
28
1
14
12
2
17
18
12
39
11
14
19
4
6
3
20

## 2. Annual Calendar Template
Annual Calendar Template
Legend
Five-Year Process
|  | INFORMATION | Key Actions
Milestone
| Implementation Task |  | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEPT | OCT | NOV | DEC | Deliverable
Meeting
Strategy & Planning
Annual Action Details
[16 empty] | 1 | 12
[16 empty] | 2 | 13
[16 empty] | 3 | 14
Information | [15 empty] | 4 | 15
[16 empty] | 5 | 16
Financial Planning & Management | [15 empty] | 6 | 17
[16 empty] | 7 | 18
[16 empty] | 8 | 19
Communications | [15 empty] | 9 | 20
[16 empty] | 10 | 21
[16 empty] | 11 | 22
28
14
12
39